**Recreation and Wellness Department Goals for 2013-2014**

|  |  |
| --- | --- |
|  | **Completion Deadline** |
| **Improve emergency skills competencies of student employees** |  |
| 1. Each program area will conduct two spot checks biweekly utilizing the Audit Team and achieve a minimum of 90% pass rate
 | On-going |
| 1. Provide mandatory remediation training for students who fail
 | On-going |
| **Add outdoor recreation facilities: high elements to the Laker Challenge Course; intramural field** |  |
| 1. Meet with contractors / receive estimates
 | Oct 2013 |
| 1. Communicate need for funding sources by meeting with External Relations
 | Nov 2013 |
| 1. Receive approval from Facilities Space Committee (if applicable)
 | Dec 2013 |
| 1. Work with Facilities and Procurement to post the RFP
 | Sept 2013 |
| **Implement a personal training program utilizing students as personal fitness trainers** |  |
| 1. Set up computer in Lisa Williamson’s office and install software
 | Sept 2013 |
| 1. Host a Personal Training certification workshop annually
 | June 2014 |
| 1. Serve at least 20 clients this year
 | June 2014 |
| **Increase intramural (IM) participation by 20%** |  |
| 1. Purchase IM magnets for marketing
 | Aug 2013 |
| 1. Market twice a month at Laker Hall and Clayton Station
 | On-going |
| 1. Utilize IM Leagues to reach constituents
 | On-going |
| 1. Compare new participation data with previous year’s data
 | May 2014 |
| **Investigate the implementation of a campus bicycle rental program** |  |
| 1. Conduct needs assessment
 | Dec 2013 |
| 1. Determine Space for maintenance and storage
 | Dec 2013 |
| 1. Contact local law enforcement about bike donation
 | Jan 2014 |
| 1. Purchase necessary tools, equipment, and supplies
 | Apr 2014 |